**The Town of Clarkson Water Improvement Benefit Area No. 1**

**June 11, 2025**

The Town’s engineers, MRB Group, have provided the following update:

* As of May 30th, the Contractor has installed approximately 54,000 linear feet of water main along portions of Drake Road, Redman Road, Monroe Orleans County Line Road, West Avenue, Old West Avenue, and Lawton Road.
* **Property owners within the water district who have signed up with the Monroe County Water Authority to receive water service are asked to mark the desired location of their water service with a wooden post. Please write the house number on the post.**
* The schedule for the remainder of the work is shown below.

**Pilon Construction Co., Inc., 13205 Route 31 Albion, NY 14411**

|  |  |
| --- | --- |
| 06/09/25 - 06/27/25 | Ireland Road main installation |
| 06/30/25 – 07/11/25 | Sweden Walker Road main installation |
| 07/14/25 – 07/18/25 | Misc connections & vault install (Drake Rd) |
| 07/02/25 – 08/29/25 | Service installation |
| 07/02/25 – 10/31/25 | Final Restoration |

* Questions: contact Scott Mattison, P.E., MRB Group, 585.340.3661.

**The Town of Clarkson Water Improvement Benefit Area No. 1**

**June 11, 2025**

The Town’s engineers, MRB Group, have provided the following update:

* As of May 30th, the Contractor has installed approximately 54,000 linear feet of water main along portions of Drake Road, Redman Road, Monroe Orleans County Line Road, West Avenue, Old West Avenue, and Lawton Road.
* **Property owners within the water district who have signed up with the Monroe County Water Authority to receive water service are asked to mark the desired location of their water service with a wooden post. Please write the house number on the post.**
* The schedule for the remainder of the work is shown below.

**Pilon Construction Co., Inc., 13205 Route 31 Albion, NY 14411**

|  |  |
| --- | --- |
| 06/09/25 - 06/27/25 | Ireland Road main installation |
| 06/30/25 – 07/11/25 | Sweden Walker Road main installation |
| 07/14/25 – 07/18/25 | Misc connections & vault install (Drake Rd) |
| 07/02/25 – 08/29/25 | Service installation |
| 07/02/25 – 10/31/25 | Final Restoration |

* Questions: contact Scott Mattison, P.E., MRB Group, 585.340.3661.